PortPro App — Work plan (TigerHawk TMS field mobile)

Content

Order by priority	2

Phase 1 – Foundation & platform (MANDATORY)	2

Phase 2 – Authentication & security	2

Phase 3 – Core driver experience	2

Phase 4 – Realtime, hardening & release	2

Rationale for time estimates	3

Phase 1 – Foundation & platform (38 h)	3

Phase 2 – Authentication & security (34 h)	3

Phase 3 – Core driver experience (62 h)	3

Phase 4 – Realtime, hardening & release (44 h)	4

Overall rationale	4

Total hours to work	4

# Order by priority

## Phase 1 – Foundation & platform (MANDATORY)

Initialize React Native (Expo or bare workflow) with TypeScript aligned to the main TMS repo standards

Establish styling baseline (e.g. NativeWind / Tailwind-for-RN) for visual consistency with the web dashboard

Implement API client layer and environment configuration targeting existing Next.js REST routes

App shell, navigation structure, and shared mobile project conventions

Estimated hours: 38 h

## Phase 2 – Authentication & security

Supabase Auth for drivers: sign-in, sign-out, and password recovery flows on mobile

Secure token/session storage, refresh handling, and deep-link callback where applicable

Enforce driver role and RLS-aware data access patterns against PostgreSQL via Supabase

Estimated hours: 34 h

## Phase 3 – Core driver experience

Assignment list and load detail views optimized for small screens and on-the-road use

Status updates using TigerHawk-validated transition APIs (e.g. Arrived at Port, In Transit, Delivered)

Document capture and upload flows (POD, Gate Pass, and related artifacts) integrated with storage/API

Estimated hours: 62 h

## Phase 4 – Realtime, hardening & release

Realtime synchronization so dispatcher changes on the web surface quickly on the device (Supabase Realtime / channels)

Integration and regression testing against staging TigerHawk TMS APIs and Supabase policies

EAS or equivalent build pipeline, internal distribution (TestFlight / Play), and pre-production hardening

Estimated hours: 44 h

# Rationale for time estimates

## Phase 1 – Foundation & platform (38 h)

React Native + Expo/CLI bootstrap with strict TypeScript (12 h) Greenfield mobile codebase; toolchain, lint/format parity with organization standards, and device simulators. No standalone backend—the app targets existing Next.js API routes and Supabase.

Navigation shell and information architecture (10 h) Driver-first flows, stack/tab navigation, and guarded routes prepared for auth. Includes baseline error and empty states.

Styling system (NativeWind or similar) (8 h) Reusable tokens, spacing, and components approach to stay visually aligned with the web TMS without copying 252 TSX components directly.

API client + environment configuration (8 h) Base URL management, authenticated fetch wrappers, typing of payloads shared conceptually with web, and handling of Next.js route conventions.

Phase 1 total: 38 h

## Phase 2 – Authentication & security (34 h)

Supabase Auth integration for drivers (14 h) Email/password or approved method, mobile-specific UX, and alignment with Supabase session lifecycle.

Secure storage and session refresh (10 h) Keychain/Keystore usage, refresh token rotation, and recovery from background/lock screen states.

RLS-aware access patterns (10 h) Validate queries respect Row Level Security for driver role; coordinate with policies defined in the TigerHawk Supabase project.

Phase 2 total: 34 h

## Phase 3 – Core driver experience (62 h)

Assignment list and load detail UI (16 h) Performant lists, pull-to-refresh, essential load metadata, and navigation into detail screens.

Status transition implementation (22 h) Mirror valid transitions from the TMS (admin/dispatcher rules); optimistic UI, confirmation dialogs, and robust error handling on API failures.

Document capture & upload (18 h) Camera/gallery permissions, compression, multipart uploads to existing document endpoints or storage patterns used by the web app.

Loading states, errors, and accessibility (6 h) Field-friendly feedback, retries on poor connectivity, and basic a11y for critical actions.

Phase 3 total: 62 h

## Phase 4 – Realtime, hardening & release (44 h)

Supabase Realtime subscriptions (16 h) Subscribe to relevant tables/channels for loads or statuses; reconcile with local state and battery/network constraints.

Cross-testing with web workflows (12 h) End-to-end scenarios with dispatchers updating loads while drivers observe changes; verify RLS and API edge cases.

Build & distribution pipeline (10 h) EAS profiles, signing, internal releases, and versioning strategy alongside the web deployment cadence.

Polish and iteration buffer (6 h) UX refinements after field feedback, minor bugfix runway before wider rollout.

Phase 4 total: 44 h

# Overall rationale

The estimates account for:

Greenfield React Native / TypeScript client: web TSX components are not portable one-to-one; business rules must be re-implemented in mobile UI while consuming the same APIs.

Backend is TigerHawk TMS (Next.js + Supabase): schedule assumes stable REST contracts; breaking API changes on the web side directly impact the mobile delivery plan.

Field conditions: camera permissions, variable connectivity, and Android/iOS fragmentation increase testing and hardening time versus a desktop-only app.

Technical stack emphasis (relevance): React Native and TypeScript as core (10/10); REST integration with Next.js routes (9/10); Supabase Auth + RLS (8/10); mobile UX (8/10); standard Git/PR workflow with the main team (6/10).

# Total hours to work

178 h